## Slide 1: DSC Delivery Sub-Group
April 20th 2026

## Slide 2
1b
1.1 Lorem ipsum
Action Updates
REC Change
NESO – Verbal Update
Previous DSG Meeting Minutes
1. General Meeting Administration

## Slide 3: 1b
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 4
SECTION 2:
Change Development
02
2a. New Change Proposals
2b. Undergoing Solution Options Impact Assessment Review

## Slide 5
SECTION 2:
Change Development
2a. New Change Proposals
2a.i Meter Read ​Service Improvements
2a.ii XRN 6065 – Minor Release 16
2a.iii XRN 6066 - Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894A)
2a.iv XRN 6067 - Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894)
2a.v XRN 6070 DDP Release 1 2027/2028
2b. Undergoing Solution Options Impact Assessment Review
2b.i XRN 5949 - New Priority Consumer Category related to Community Heating
2b.ii XRN 5473 - Meter Asset Comparison Service

## Slide 6: Meter Read Service Improvements
Information Update - ChMC

## Slide 7: Meter Read Service Improvements
Part | Title | Delivery Approach | DDCP | BER
A | Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution | MiR16 | N/A | N/A
B | Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution | MiR17 | N/A | N/A
C | NDM Check to Check Reconciliation – Enduring Solution | Nov 26 Major Release | TBC | TBC
D | Reconciliation of Multiple Read Replacements – Enduring Solution | TBC | TBC | TBC
E | Read Inserted Prior Expected Class 4 Opening Read - Volume and Energy Calculation | TBC | TBC | TBC
F | Read Validation where no Actual Read Present in Previous Class Period | TBC | TBC | TBC
G | Reconciliation of Class Change with subsequent Shipper Transfer and Class Change | TBC | TBC | TBC
H | RGMA Read Validation where Site Flagged as AMR | TBC | TBC | TBC
I | NDM Opening Read Estimation Based on Read with a Positive Through The Zero Count | TBC | TBC | TBC
J | Twin Stream Volume Aggregation | TBC | TBC | TBC
Several Service Improvement changes have been identified within CDSP meter reading processes. This update seeks to provide visibility of these changes, highlight the proposed delivery approach for each change & to seek ChMC approval where it is found that changes would benefit from inclusion in a Major Release
Notes: Add bullets

## Slide 8: Meter Read Service Improvements
Service Improvements | Description
Part A & C | Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution (A) / NDM Check to Check Reconciliation – Enduring Solution (C)
Issue | For Class 3 and 4 sites with AMR equipment, the system should perform Check to Check (C2C) reconciliation when a site visit or RGMA actual read is received. This reconciliation must be based on the prevailing consumption which can be: Deemed allocated position (if no reads exist), or Actual consumption (if readings exist), or A combination of both (if partial readings exist). Current system logic always uses the deemed allocated volume/energy, ignoring actual readings.
Change | The system to consider both deemed and actual consumption when performing C2C reconciliation and align with UNC Section E6.2, ensuring reconciliations are based on actual usage where data is available.
Impacts | The current process miscalculates reconciliations and causes incorrect energy volumes to flow into UIG (Unidentified Gas). Invoice charges do not reflect true consumption. The system logic is not aligned to UNC rules. Invoicing teams face growing volumes of queries and are manually correcting consumption via adjustments.
Benefits | Accurate, first-time billing. Correct energy allocation into UIG. UNC compliance — reconciliations reflect prevailing consumption. Reduced Shipper queries and faster resolution. Reduced manual intervention for both CDSP and Shipper customers.
Part B & D | Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution (B) / Reconciliation of Multiple Read Replacements – Enduring Solution
Issue | The reconciliation process is incorrectly handling multiple shipper readings submitted on the same date, received via inbound read files (UMR/UBR/Must reads) and RGMA replacement read files (RRP) files. The system does not necessarily calculate based on the first read received, instead choosing a subsequent or replacement reads submitted later that day. This results in incorrect consumption calculations, inaccurate reconciliations, and incorrect invoicing. The system does not correctly recognise or prioritise replacement reads submitted on the same date. Reconciliation runs before later reads are factored in, using outdated or invalid data.
Change | Update reconciliation logic to correctly handle and prioritise multiple/replacement reads submitted on the same day. Apply to all classes and read sequences. Profile issue extent, review batch job dependencies (UMR, RRP, REC), and quantify volumetric impact.
Impacts | Customers receive incorrect invoices and inconsistent reconciliation data, triggering a high volume of queries and loss of confidence in billing accuracy. Manual workarounds by the reads team when raised by the customer, causing delays and inefficiency. Incorrect energy position fed into UIG reconciliation, affecting all market participants. Financial risk due to over- or under-reconciliation. Non-compliance of UNC E6.2.1B – as Reconciliation not based on the correct metered period or values.
Benefits | Accurate reconciliations reflecting the latest valid reads. Fewer invoice and UIG errors. Reduced customer queries and restored confidence in system reliability. current system produces inaccurate reconciliations and invoices, directly impacting customers financially while being misaligned with rules (UNC E6.2.1B). Fixing ensures accurate billing, and system compliance, while removing the need for time-consuming manual workarounds.
Service Improvements | Description
Notes: Add bullets

## Slide 9: Meter Read Service Improvements
Service Improvements | Description
Part E | Read Inserted Prior Expected Class 4 Opening Read - Volume and Energy Calculation
Issue | When a read from the outgoing shipper is received for D-1 (class 4 shipper transfer or shipper transfer with a class change, leaving class 4) the read is marked inactive and not used in downstream processing. If another read (inserted or replaced) for a date before D-1 is later received before the transfer read is fulfilled (estimate or actual), the system fails to update the next read date and next read volume against the inserted/replaced read (since the next read is an inactive read) nor is the volume revised against the inactive read. Consequently, when the transfer read is then estimated at the end of transfer window (i.e. D+11) or earlier due to receipt of another read within the transfer window, the estimated transfer read and volume calculated is incorrect.
Change | When a read is inserted or replaced before an inactive read, the system must revise the volume for the inactive read and correctly reflect the next read date and volume against the inserted/replacement read, so that the transfer read estimation uses the correct data.
Impacts | Potential financial impact to the customer as incorrect transfer reads will be issued to the outgoing and incoming Shippers thereby potentially impacting processes such as incorrect reconciliation and inaccurate AQ Calculation. There is an ask on the customer to replace any estimate or incorrect actual read, which would turn the negative into a positive, meaning that the customers would be fixing this issue without our assistance.
Benefits | Correct reconciliation and billing for both shippers. Accurate AQ calculations. Correct transfer reads issued to outgoing and incoming shippers.
Part F | Read Validation where no Actual Read Present in Previous Class Period
Issue | When a new read is received after a class change (or when a class change estimated read is replaced) the system validates it only against the previous actual read from the immediate previous class. If no actual read exists in that class the read may be rejected with error MRE00430 – “The Meter Point has no previous read.”, or the estimated class change read may be incorrectly treated as an actual read for validation. This design limitation stems from the Nexus implementation, where DM sites became Class 1 and NDMs became Class 4, and validations were intentionally restricted to only one previous class.
Change | Read Validation to look further back in the read history, to validate read submissions to actual readings, not estimated. There may be additional scenarios impacted.
Impacts | As class changes (especially 4↔3) increased after MOD700 and with ongoing mass migrations and CSS, the issue became more prevalent. Common scenario - rapid class changes (e.g., Class 4 → 3 → 4 within two days) lead to high chance of no actual read in the previous class. Resulting in read rejections or incorrect validation. Read performance degradation, inaccurate AQ calculations, billing errors, UIG impacts, Increased Shipper Agreed Read rejections when class change coincides with shipper transfer
Benefits | Reduce the number of incorrectly rejected shipper reads. In addition, where reads are not rejected but validated against a Class Change estimate, we are in contradiction of the UNCVR rules. In this situation the Shipper will be validating the submitted read against a different read to the CDSP which could lead to different rejection.
Service Improvements | Description
Notes: Add bullets

## Slide 10: Meter Read Service Improvements
Service Improvements | Description
Part G | Reconciliation of Class Change with subsequent Shipper Transfer and Class Change
Issue | An issue currently exists in UKLink (SAP ISU) where an account is undergoing a class change (CC) from Class 3 to Class 4, and subsequently a Class Change + Shipper Transfer (CC+ST) occurs immediately one day later from 4 to 3, the FICC read which is supposed to be created on D-1, is being replaced by a FINT read. FICC read initiates reconciliation activity hence in this event reconciliation is not initiated impacting billing. Exceptions are being generated and associated to this issue.
Change | The system must be updated to generate and reflect a FICC read for a class change at D-1 of a Shipper Transfer and class change, so that reconciliation can be triggered.
Impacts | The current process means reconciliation is not triggered for these sites, so there is a 1-day Rec missing and the customer is not being billed, resulting in financial disparity (positive or negative), impacts to UIG reconciliation.
Benefits | Settlement values will be correct for affected sites (feeding UIG correctly) and customers will receive accurate invoices.
Part H | RGMA Read Validation where Site Flagged as AMR
Issue | An issue currently exists in UK Link (SAP ISU) when a registered user submits an RGMA Activity with reads, where an AMR Device (Automated Meter Reading device) is also installed. Any RGMA Activity received with reads should validate back to the last actual Check Reading (Site Visit Read). The system is incorrectly identifying estimated Shipper Transfers as the last Check Read as part of read and energy tolerance validation. These newly received RGMA readings are in some instances being incorrectly rejected or accepted. Connected to Service Improvements Part F.
Change | RGMA Read Validation will work as intended in first time processing, resulting in fewer queries and manual workaround.
Impacts | Impact Customer satisfaction. An increase to the number of queries with this issue requiring the workaround, which will increase the time it takes to complete. RGMA transaction will be incorrectly accepted or rejected based on current rules. Read validation processes for Site Visits, regardless of the source of data, remain inconsistent.
Benefits | Improvement of our Customer’s Experience. Reduction in the number of Reads/RGMA Queries received, as this would remove this particular issue that the customer is raising. Faster response time to queries raised (where manual intervention is currently required, this increases the time it takes to resolve). Removes the manual workaround for incorrect RGMA Read Validation.
Service Improvements | Description
Notes: Add bullets

## Slide 11: Meter Read Service Improvements
Service Improvements | Description
Part I | NDM Opening Read Estimation Based on Read with a Positive Through The Zero Count
Issue | Issue identified whereby NDM estimation, for a shipper transfer, is incorrectly including the provided TTZ. As part of read processes, it is mandatory for the submitting organisation to provide the TTZ. The TTZ is the value the metering device has clocked since the last actual read and is used in validation of the read and calculation of consumption. In this scenario a read is received within the transfer read window, with a read date other than the transfer date. This read is utilised by NDM estimation to create an estimated transfer read, volume and energy. Where a TTZ other than zero, has already been applied to previous estimated readings and no subsequent actual is present, the volume and energy for the outgoing and incoming Shipper is incorrect. The TTZ used to calculate current volume is derived by TTZ of the Current Read minus The SUM of all TTZ values between Last Actual Read and the Current Read
Change | To ensure the read data provided is used correctly in the calculation of a transfer meter read, metered volume and energy.
Impacts | A work around is currently in place where monthly profiling is carried out and the reconciliation period is corrected via a consumption adjustment. Therefore there is no current impact to customers as corrections are made before invoice issue.
Benefits | 1. Application Support no longer required to carry out monthly workaround -profiling and correcting consumption. 2. Adherence to first time right principle, with estimated reads and consumption being generated correctly.
Notes: Add bullets

## Slide 12: Meter Read Service Improvements
Service Improvements | Description
Part J | Twin Stream Volume Aggregation
Issue | The current system set up is not correctly converting the aggregated volume to energy on Twinstream sites. It is not using the FWACV and appears to be using the previous days value. It is also not including amendments to the CV it uses. The CON file is sent from ISU to Gemini on a daily basis. The batch job for aggregation of DM measurements that is sent in the CON file is run after the Energy Recalculation report is run for that particular day, and updates the energy based on the CV value received in the CVV file which may contain amended CV data for which energy might have already been calculated earlier in the day. It has been identified that this is not happening for twin stream sites where there is an aggregator attached. As a result of this, the aggregated energy on a twin stream setup is not reflecting the sum of the energy for both streams when there is amended CV data. It is this aggregated meter profile which is being passed to Gemini for allocation and thus impacting Shipper's invoicing and UIG. It is understood to impact a subset of Twinstream sites. Energy using the updated CV for a Gas Day is only being updated on the individual convertor devices' energy profiles and not updating the energy using the updated CV on the aggregator's energy profiles, causing a mismatch in energy between the individual energy profiles and the aggregator energy profile.
Change | We are unsure how many MPRs are impacted as site configuration arrangements are often unique per set up.
Impacts | Incorrect aggregated energy values, which impacts the Shippers invoicing, Unidentified Gas and the Gemini Processes.
Benefits | Aggregated Energy is correct with no mis-matches, Invoicing, UIG and reporting are correct.
Notes: Add bullets

## Slide 13: Meter Read Service Improvements
Next Steps
A Service Improvements Change Proposal to be raised to provide visibility of all changes; to be supplemented by individual Change Proposals as required.
Regular Service Improvement project update to be provided at ChMC to share progress of these changes through the Change lifecycle & to highlight proposed delivery approach, inclusive of any proposed customer consultations (e.g. design change packs).
Approval to be sought where it is identified that changes impact customers and / or benefit from inclusion in a Major Release (e.g. due to complexity and degree of test / PIS assurance activities).
Notes: Add bullets

## Slide 14: XRN 6065 – Minor Release 16
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | 
This vote is to approve the change into development | 
Change Type | Non-Regulatory
Priority | Medium
Proposer | CDSP​
Change Proposal | Link to CP
Change Description
This change proposal has been raised to create a parent XRN for the Minor Release Drop 16 There is 1 change within this release: Meter Read Service Improvements – Part A Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution The current check to check process miscalculates reconciliations and causes incorrect energy volumes to flow into UIG (Unidentified Gas). Invoice charges do not reflect true consumption. In turn, system logic is not aligned to UNC rules. Invoicing teams face queries and are manually correcting consumption via adjustments. This change will fix incorrect check to check reconciliation periods historically and will provide an interim solution until the enduring change has been implemented.
DSC Service Area Associated Funding Split | Service Area : N/A
Proposed Funding split from Proposer | Minor Releases form part of the Service and Operate (S&O)

## Slide 15: XRN 6066 - Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894A)
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | 
This vote is to approve the change into development | 
Change Type | Regulatory
Priority | High
Proposer | CDSP​
Change Proposal | Link to CP
Change Description
This change is seeking to enable the flow of gas from a downstream LDZ to the NTS which in turn would provide LDZ capability that would facilitate Biomethane entry into the GDN. DNOs and NTS are considered impacted parties due to changes involving the creation of a new LDZ/NTS Delivery Point enabling gas flow from an LDZ into the NTS to support additional LDZ Entry capability will have impacts for both DNOs and the NTS. DNOs are further considered as impacted due to the impacts to FWACV calculation and associated processes. Shippers have been identified.
DSC Service Area Associated Funding Split | Service Area : 10, 17 & 14
Proposed Funding split from Proposer | TBC

## Slide 16: XRN 6067 - Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894)
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | X
IGTs | 
This vote is to approve the change into development | 
Change Type | Regulatory
Priority | High
Proposer | CDSP​
Change Proposal | Link to CP
Change Description
This change is seeking to Facilitate Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression. DNOs are considered as impacted as the change will create a new type of offtake from a DNO to the NTS in order to free up additional LDZ Entry Capacity. To ensure that all gas offtaken is correctly recorded DNOs will see changes to the existing BAU process. Shippers are considered an impacted party because they will be notified of any corrected values as part of agreed reconciliation process. NG have also been identified. Although there are no Gemini impacts expected by the delivery of this Change Proposal, the Modification in general has impact because it is transportation of gas into the NTS.
DSC Service Area Associated Funding Split | Service Area : 10 & 17
Proposed Funding split from Proposer | TBC

## Slide 17: XRN 6070 DDP Release 1 2027/2028
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | X
This vote is to approve the change into development | 
Change Type | Non-Regulatory​
Priority | Medium​
Proposer | CDSP​
Change Proposal | Link to CP
Change Description
The request for this Change Proposal is to ensure that there is visibility to ChMC of the changes within scope of DDP Release 1 2026/27 – this aims to provide transparency so the rationale of the priority being applied to DDP scope can be clearly understood. Release 1 will build on the analysis and design work in Release 6, and will begin development for multiple reports within the PARR which will be modified as described under these changes: • XRN5923 – Updates to the PARR • XRN5992 – HPM Report Changes • UNC MOD0884
DSC Service Area Associated Funding Split | Funded via annual DSC DDP change delivery costs, which forms part of the General Change Investment within BP26​​
Proposed Funding split from Proposer | N/A

## Slide 18
2b. Undergoing Solution Options Impact Assessment Review
2b.i XRN 5949 - New Priority Consumer Category related to Community Heating – Change Pack

## Slide 19: XRN5473 – Meter Asset Comparison Service
High Level Solution Options

## Slide 20: XRN5473 Change summary
Background
Following the implementation of XRN4780-C, Meter Asset Managers (MAMs) and Meter Equipment Managers (MEMS) were required to provide meter asset transaction data to the Central Data Service Provider (CDSP).
XRN5473 has been raised to investigate, and develop, a comparison service to assess the asset data received from MAM/MEMs against those held on the Supply Point Register, received from the Shipper User.
The service aims to identify inconsistencies in meter asset data that could lead to
settlement issues, enabling customers to take proactive corrective action to improve
overall data quality.
Notes: Add bullets

## Slide 21: XRN5473 Change summary
As-Is:
MAM/MEM parties submit asset data to CDSP systems and this is stored in the “MAM Store”. Shipper parties submit asset / RGMA data to CDSP systems and this is stored in the “Supply Point Register”. Currently these data stores are not cross-referenced or compared.
To-Be:
The introduction of this service will enable the comparison of the data held in MAM Store and Supply Point Register, for the data items selected as part of the ‘MVP’. The data items and outcomes of the comparison service will be shared with consumers of the service (Shippers and IGTs). The data items defined as part of the MVP include:
Installed MSN
Multiplication Factor
Unit of Measure
Number of dials
Converter Correction Factor
Meter Mechanism Code
Payment Method Code
Asset Class Code
Converter Serial Number
Notes: Add bullets

## Slide 22: XRN5473 High Level Solution Option 1
MAM / Shipper
Asset and RGMA data flows
UK Link
MAM and Shipper Data Stored
# | Description | Systems and process impacts | Cost Estimate Range
1 | DDP Power BI / Birst Dashboards – reporting and visuals Data loaded and transformed inside DDP processing layer | DDP Replication Layer / Processing Replication of MAM Store data Comparison Programs of 9 ‘Must Have’ data items between MAM Store and Supply Point Register DDP Visualisation Hosted on a Fabric premium capacity / Birst database(s) DDP Dashboard featuring: Mismatch summary statistics and volume metrics, Interactive filtering by data field, mismatch type, and Shipper, Registered Shipper identification, Data freshness indicators with last update timestamps, Time gap calculation between MAM updates, Supply Point Register updates and Historical tracking of data synchronization patterns. Drill-down capabilities including: ▪ Side-by-side comparison view (MAM vs Supply Point Register) ▪ Field-level mismatch highlighting and identification ▪ Individual MPRN record analysis ▪ Temporal analysis showing update gaps and time periods Eligible with DDP subscription | Delivery: £21k to £36k
DDP Replication
MAM and Shipper Data Stored
DDP Processing
Data Comparison Scripts
Consumer
Access to dashboards and reporting
DDP Visualisation
New dashboards highlighting comparison outcomes

## Slide 23: XRN5473 Option 1 Functionality
Functionality ‘Deeper Dive’:
Comparison Engine
  Field specific validations
  Exact match comparison algorithms
  Missing data detection and classification
Reporting
  Mismatch summaries statistics and volumes
  Interactive filtering by Consumer, data field, mismatch type
  Data ‘freshness’ indicators with timestamps
Drill-Down
  Side by side comparison views (MAM Store data to Supply Point Register data)
  Field Level mismatch highlighting
  Individual MPRN record analysis
Role based visibility and permissions
Notes: Add bullets

## Slide 24
XRN5473 – Proposed delivery timeline – Option 1

## Slide 25: XRN5473 High Level Solution Option 2
MAM / Shipper
Asset and RGMA data flows
UK Link
MAM and Shipper Data Stored
# | Description | Systems and process impacts | Cost Estimate Range
2 | Standalone comparison service hosted on Azure with Power BI visualisations layered for customer consumption | Azure hosted data lake Replication of UK Link data loaded at defined frequency required to enable comparison (suggest daily) ELT of asset data from Supply Point Register (6 tables) and MAM Store to enable comparisons Scripts to run comparisons of MVP data items Power BI visualisation: Dashboards hosted on Microsoft Fabric workspace to enable external consumption Role based access allows consumers to see only what they are allowed to Visualisations of comparison and drill down Paginated reporting optional to allow download of data from dashboards | Delivery: £270,000 - £570,000 Ongoing: c£5,000 - £10,000 for Fabric capacity licences (Prod and Pre-Prod) per month
Data Lake
Azure hosted
Transformation layer
Azure database processing
Consumer
Access to dashboards and reporting
Power BI Visualisations
Standalone service

## Slide 26: XRN5473 – Option comparison
# | Description | Systems and process impacts | Cost Estimate Ranges | Option Pros | Option Cons
1 | DDP | DDP Replication Layer / Processing - Replication of MAM Store data Comparison Programs DDP Visualisations – DDP dashboards with comparison visualisations | £21k to £36k | Re-use of current DDP infrastructure and tooling Inbuilt security, permission, and access controls Already native to industry users | Delivery will need to fit around existing DDP delivery sprints
2 | Standalone comparison service | Azure Hosted Data lake - Replication of UK Link data Scripts to run comparisons of MVP data items Power BI visualisation - Dashboards hosted on Microsoft Fabric workspace | £270k - £570k c£5,000 - £10,000 monthly ongoing costs | Greater flexibility in the future scope of tool with visualisations, customer interactivity and wider integrations not determined by DDP roadmap. | Creation and ongoing maintenance of new access controls, security standards and BCM for new data service Further replication of UK Link data to another data store Customer sign up, and training, required for new data service

## Slide 27: XRN5473 Assumptions, Dependencies, Risks
Category | Description
Assumption | A daily data refresh should provide sufficient latency for customer to perform, and be updated on, data comparisons.
Assumption | This iteration of this service will operate as ‘for information’
Risk | There is an ongoing risk of data quality of the MAM Store as minimal validations occur on the data input and the timing of asset data submissions between MAMs and Shippers.
Risk | If the service is built on the current DDP visualisation tool, there is a risk of additional technical debt and efforts required to rebuild the service post visualisation upgrade.

## Slide 28
SECTION 3:
Detailed Design
03
3a. Design Considerations
3b. Requirements Clarification
Project Updates

## Slide 29
SECTION 3:
Detailed Design
None for this meeting
3a. Design Considerations
3b. Requirements Clarification
3b.i XRN 5805 - Alternative Solution to address instances where VBA macros are present in DN Templates - Design Clarification

## Slide 30: XRN 5805 Alternative Solution to address instances where VBA macros are present in DN Templates
Design Considerations

## Slide 31: Update to Design (File Size Limits)
Largest Output file received in production​ over the last 2 years ​ | 
FSG​ | 467 KB​
RTB​ | 148 KB​
TSI​ | 15 KB​
ORD​ | 3 KB​
BCL​ | 1.72 MB​
We are seeking to update the XRN5805 design so that templates uploaded to the Portal can be no larger than 4MB in size.
The initial design was to allow input templates up to 15MB in size so that this was aligned with the maximum file size for CMS upload. However, this limit should have been the maximum output file size (Portal to CMS), not input template size (file submitted to Portal). Due to the optimisation of .xlsx files compared to .csv files, an input .xlsx template generated as a .csv file can triple in size.
Therefore, if the input template limit is not reduced the Portal may allow an output file to be generated that is larger than the CMS acceptable limit, or the acceptable limit for email attachment (30MB).
A 4MB limit should mean all input templates result in an output file generated below 15MB that will pass any further downstream validations. On the right is a Matrix displaying the largest output files received over the last 2 two years for selected templates.

## Slide 32: Update to Design (File Size Limits As-Is, To-Be)
Upload Template
UKL Portal
File Size Validation: Input File <= 15MB
Reject file and display rejection message
DNs
Create Output file (up to > 50MB)*
Upload Template
UKL Portal
File Size Validation: Input File <= 4MB
Reject file and display rejection message
DNs
Create Output file (up to > 15MB)**
X
X
*May fail CMS upload, May fail email size limitations.
**Will pass CMS upload, Will pass email size limitations.
.csv
.xlsx
.csv
.xlsx
.xlsx
.xlsx

## Slide 33: Actions and Next Steps
Relevant updates will be made to the internal Design documentation and training material.
There is no additional cost or timeline changes.
For the avoidance of doubt, the detailed design change pack will not be reissued given the actions being take i.e. this DSG update and updated training material

## Slide 34
Section 4: Release/Project Updates
04
4a. Feb 26 Major Release
4b. June 26 Major Release

## Slide 35: XRN 5983 – February 26 Major release - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of February 26 Major Release was presented for approval at the ChMC meeting on 10/09/25. Overall release is tracking to target. Project was successfully implemented, 27/02/26, Post Implementation Support expected to complete 10/05/26. Progress Update: XRN5906, 5872, 5914/5922 are in Post implementation support (PIS) PIS has been extended to 10/05/26 to include the LIS shortening 01/04/26 and the new rolling LIS period 01/05/26. | Implementation date 27th February, contingency date 6th March | 
Risks and Issues | N/a |  | 
Costs | Changes are currently delivering with projected costs. |  | 
Scope | XRN5906 - Extending the PC4 Read Submission Window. XRN5872 - Updates to the AQ Amendments Process. XRN5914/XRN5922 - Shorten of the current LIS (Line in sand) date to 2-3 years & amend the LIS to rolling Period. |  | 
Complete
On Track
At Risk
Overdue

## Slide 36: XRN 6045 – June 26 Major Release - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of June 26 Major Release was presented for approval at the ChMC meeting on 11/02/2026. Overall release is tracking to target; project is planned implement on 26/06/2026. Progress Update: XRN5805 has exited Design and is due to start build on the 13/04/2026 XR5702 is currently working through closure of Design post a revalidation exercise and is due to close on the 27/03/2026 Decision in April ChMC: None | Implementation date 26th June 2026, contingency date 3rd July 2026 | 
Risks and Issues | N/A |  | 
Costs | Forecast to complete delivery against approved BER |  | 
Scope | XRN5702 – Update to assess the replacement of Facsimile as a form of communication (Modification 0864S) XRN5805 - Alternative Solution to address instances where VBA macros are present in DN Templates |  | 
Complete
On Track
At Risk
Overdue

## Slide 37
Section 5:
Change Pipeline
05
Change Pipeline

## Slide 38: 2026 Forward View - Change Delivery Plan
January 26 – December 2026
Jan-26
June-26
February 26 – Major Release (XRN5983)
XRN5872 | XRN5906 | XRN5914 | XRN5922
March-26
Sep-26
Dec-26
June 26 – Major Release (XRN6045)
XRN5702 |XRN5805
Slide produced 29h July 2025
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding not yet approved by ChMC
= Implemented Change / Release
November 26 - Major Release
XRN5940| Meter Read Service Improvements (Part C)
XRN5994 - Emergency Contact Data Service
Identifying Improvements to Meter Point Location Address Data Processes
XRN5968 | XRN5546
Minor Release 18
MiR17 - Service Improvements Part B
MiR16 - Service Improvements Part A
PIX
5924
XRN5941 – Performance Assurance Committee - Audit PAT
XRN6041 - CDSP Obligations required for the introduction of the Gas Shipper Obligation

## Slide 39: Change Delivery Plan – January 2026 – December 2026
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Delivery Date | Release Type | Firm / Indicative
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | Shipper | £190k | 27 February 2026 | Major | Firm
5906 | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | Shipper DN | £105k | 27 February 2026 | Major | Firm
5914 5922 | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SSE SEFE | Shipper DN IGT | Shipper | £90k | 27 February 2026 | Adhoc / Major | Firm
5941 | Performance Assurance Committee – Audit PAT | Xoserve | Shipper DN IGT | Shipper DN IGT | £300K | TBC | Adhoc | Indicative
5994 | Emergency Contact Validation Service | Cadent | Shipper DN | tbc | TBC | May 2026 | Adhoc | Indicative
6065 | Meter Read Service Improvements Part A Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution | Xoserve | Shipper DN | N/A | N/A | 12 June 2026 | Minor | Indicative
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | Shipper DN | £158k | 26 June 2026 | Major | Firm
5805 | Alternative Solution to address instances where VBA macros are present in DN Templates | WWU | DN | DN | £160k | 26 June 2026 | Major | Firm
5924 | Physical Information Exchange (PIX) Ongoing Support Options | Xoserve | All | TBC | N/A | 31 June 2026 | Adhoc | Firm
TBC | Meter Read Service Improvements Part B Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution | Xoserve | Shipper DN | N/A | N/A | September 2026 | Minor | Indicative
5949 | New Priority Consumer Category related to Community Heating (Phase 1) | NGT | All DSC Customers | TBC | TBC | September 2026 | Adhoc | Indicative
5940 | Mod0890 – Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation | Centrica | Shipper DN | TBC | £270k | 6 November 2026 | Major | Indicative
TBC | Meter Read Service Improvements – Part C NDM Check to Check Reconciliation – Enduring Solution | Xoserve | Shipper DN | Shipper DN | £110K | 6 November 2026 | Major | Indicative
6041 | UNC Modification 0922 (IGT UNC Modification 180) – CDSP Obligations required for the introduction of the GSO | CDSP | ALL DSC Parties | Shipper | TBC | December 2026 | Adhoc | Indicative

## Slide 40: Change Backlog – ‘In Progress’ Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | April 26 - ChMC Update
6001 | Modification 0909 - Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures | SEFE | Shipper DN | Shipper DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
6000 | Modification 0908 – Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading by a Shipper | WWU | Shipper DN IGT | DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
5972 | CDSP provisions to support new Supplier Deed of Undertaking (DoU) Licence Condition (9a) | Cadent | DN IGT | DN | Requirements | Change Proposal raised on behalf of DNs to ensure new Deed of Undertaking arrangements are put in place with Supplier organisations. Analysis on Invoicing processes (charge types) to be performed and validated with DNs.
5987 | Modification 0915 – Debt Relief Scheme Payment (DRSP) | NGN | Shipper DN IGT | NGT DN | Requirements | CDSP will be actively supporting Modification development over proceeding months ahead of baselining requirements.
5473 | Meter Asset Comparison Service | CDSP | Shipper | Shipper | Requirements | Use cases, data items and research being undertaken by development team ahead of options being presented to DSC members – target Q2 2026 update for DSC customers at DSG
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Solution Assessment | Solution Option issued for consultation in May ‘25 Change Pack – next steps to be confirmed following change pack decision and agreement on how to progress.
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Solution Assessment | Protype solution being trialled with one DN party ahead of finalising functionality and sharing with all DN parties. Workshop arranged 3rd October. Continue to monitor progress with DNs before reaching agreement that change can be closed.
5950 | DSC Invoice Number generation review | CDSP | Shipper DN NGT | TBC | Solution Assessment | Re-assigned to change backlog as change is not time critical and will require customer notification period prior to delivery. Solution Option Change Pack targeted in May.
5955 | Private networks duplicate MPRNs - options for long-term fix | Cadent | DN | DN | Solution Assessment | Re-assigned to change backlog ahead of Solution Option Change Pack being published in May for consultation.
5968 | Identifying improvements to Meter Point Location Address Data processes | Cadent | DN | DN | Analysis | Parent Change Proposal raised to perform analysis and make recommendations on changes that can be implemented to the Address Amendment process.
6039 | Provision of IGT SMP Data to DNs | NGN | DN IGT | DN | Requirements | Change Proposal raised to progress solutions that enable DNs the ability to receive IGT SMP data.
6056 | Introduction of new Supply Meter Point status of ‘IS’ (Isolation) - Cleanse and remove obsolete ‘CL’ (Clamped) status | Cadent | DN IGT Shipper | DN | Requirements | New Change Proposal raised to progress solution that enables DNs and other industry stakeholders the ability to acknowledge a Supply Meter Point Status of Isolation.

## Slide 41: Change Backlog – ‘On Hold’ Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | April 26 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Agreed following August bi-party CSEP meeting that change will remain on hold whilst data cleansing activities were progressed.
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | N/A | N/A – performing analysis on data extracts provided by DCC Next steps to be confirmed once analysis is concluded
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | TBC | Low Priority – CDSP raised Change Proposal
5701 | Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert (Modification 0843 / IGT 165) | OVO | Shipper DN IGT | DN IGT | TBC | Recommend that change remains on. No development activities will take place until Ofgem decision on Modification is received.
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | TBC | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource

## Slide 42: DSC Change Pack Consultation Plan (two-month view)
Apr – 26
May - 26
Jun – 26
XRN5955 - Private networks duplicate MPRNs - options for long-term fix
Key
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
XRN5949 - New Priority Consumer Category related to Community Heating
XRN5950 - DSC Invoice Number generation review
XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (Modification 0890)
XRN5937.3 - Facilitating Bi-Directional Connections Between IGT pipelines and the NTS (Modification 0887)
XRN5473 - Meter Asset Comparison Service

## Slide 43
Section6: AOB
06
Any Other Business

## Slide 44
Section 7:
Annex
07
7a. ChMC Update
7b. REC Update
7c. POAP