## Slide 1: DSC Delivery Sub-Group
June 2026

## Slide 2
1b
1.1 Lorem ipsum
Action Updates
REC Change
NESO – Verbal Update
Previous DSG Meeting Minutes
1. General Meeting Administration

## Slide 3: 1b
The DSG Actions Log will be published on the DSG pages of Xoserve.com

## Slide 4
SECTION 2:
Change Development
02
2a. New Change Proposals
2b. Undergoing Solution Options Impact Assessment Review

## Slide 5
SECTION 2:
Change Development
2a. New Change Proposals
XRN 6095 November 2026 Major Release (Parent Change)
XRN 6096 DDP Release 2 2026/2027
2b. Undergoing Solution Options Impact Assessment Review
None for this meeting

## Slide 6: XRN 6095 November 2026 Major Release (Parent Change)
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | X
This vote is to approve the change into development | 
Change Type | Non - Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP
Change Description
This change proposal has been raised to create a parent XRN for the November 26 Major Release There are 2 changes within this release: XRN 5940 Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (Modification 0890) XRN 6081.C - NDM Check to Check Reconciliation – Enduring Solution
DSC Service Area Associated Funding Split | N/A
Proposed Funding split from Proposer | Funding details will be itemised for each change within the Business Evaluation Report (BER) ​

## Slide 7: XRN 6096 DDP Release 2 2026/2027
Customer Parties | Impacted parties
Shipper | X
Distribution Network Operators (DNOs) | X
National Gas Transmission | 
IGTs | X
This vote is to approve the change into development | 
Change Type | Non – Regulatory
Priority | Medium
Proposer | Xoserve
Change Proposal | Link to CP
Change Description
The request for this Change Proposal is to ensure that there is visibility to ChMC of the changes within scope of DDP Release 2 2026/27 – this aims to provide transparency so the rationale of the priority being applied to DDP scope can be clearly understood. Following prioritisation discussions at ChMC, in release/sprint 2 (Jun-Jul), we intend to continue work on updates to the PARR Reporting within DDP. Release 2 will build on the analysis and design work in Release 6 & Release 1, which began development for multiple reports within the PARR which will be modified as described under these changes: •XRN5923 – Updates to the PARR •XRN5992 – HPM Report Changes •UNC MOD0884
DSC Service Area Associated Funding Split | Funded via annual DSC DDP change delivery costs, which forms part of the General Change Investment within BP26
Proposed Funding split from Proposer | N/A

## Slide 8
SECTION 3:
Detailed Design
03
3a. Design Considerations
3b. Requirements Clarification
Project Updates

## Slide 9
SECTION 3:
Detailed Design
XRN 5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (Modification 0890)
3a. Design Considerations
3b. Requirements Clarification
None for this meeting

## Slide 10: XRN 5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890S)
Detailed Design Pack Summary - DSG

## Slide 11: XRN 5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890S)
Background:
UNC currently stipulates an AQ is calculated in an ‘AQ Calculation Month’ only where a Qualifying Meter Reading is received. Currently, when a Request For Adjustment (RFA), Consumption Adjustment or a Replacement Read is submitted for a Supply Meter Point (SMP) the AQ does not recalculate without receipt of a subsequent Qualifying Meter Reading.
For the AQ to be updated a Shipper must submit post accepted reads to UK Link and in the absence of customer readings, this could lead to an inaccurate AQ for an extended duration of time.
This change is seeking to introduce the addition of valid consumption adjustment and valid updated meter readings to initiate an AQ Calculation or AQ Revision as applicable. When Consumption Adjustments and Replacement Meter Reads meet the relevant criteria, they will be considered for the AQ recalculation sooner and with less effort or impact on the Shipper.
This change seeks to adopt consistent logic across CDSP systems and services, as this would enable data that is already being provided and validated by the CDSP to be used in downstream AQ processes.
Shippers have been identified as an impacted party, as they have requested this capability in the related UNC Modification (0890S). Networks, including IGTs have also been identified as impacted, as the related industry rules will require the CDSP to include two new triggers in AQ calculation or AQ revision processes.
In Scope:
# All site types are intended to be in scope of this change.
# All types of valid accepted updated meter reads for class 2, 3, 4 supply points (Class 1 actual meter reads cannot be updated).
# All types of valid accepted consumption adjustments for all supply point classes (including any energy adjustments for Telemetered sites)
Out of Scope:
# Consumption adjustment reasons ‘isolation’ and ‘duplicate’.
# Changes to Winter Consumption calculation.
# Changes to AQ correction.
# Changes to upstream processes with regards to how updated meter reads or consumption adjustments are received in UK Link
# Any consumption adjustments processed outside UK Link

## Slide 12: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890S)
Change summary:
This change will introduce new concepts of “AQ Revision”, “primary and secondary AQ triggers” and “AQ trigger type” within the monthly AQ review process.
Changes will be made to the existing rolling AQ calculation process for primary reading trigger determination where the latest qualifying read is due to an updated meter read or has an adjustment applied to it.
A new AQ revision process will be introduced for including secondary triggers i.e. consumption adjustment and updated meter readings.
A new AQ trigger type will be introduced as an internal value to identify all primary and secondary AQ triggers.
New validation checks will be needed to ensure only valid adjustments and replacement reads which fall within the latest AQ relevant metered period are treated as valid triggers.
Changes to identify primary and secondary triggers in case of multiple triggers to decide between AQ calculation vs AQ revision
New internal failure texts will be introduced to record any AQ revision failures; however, these will not be notified externally
Changes to AQ NRL notification process to ensure the new internal AQ trigger type is not reported externally via T04 segment. No change to the NRL file format.
New AQ methodology code for AQ revision will be introduced for external reporting via the MPRN misuse report sent to the PAC
Changes to internal AQ tools and internal AQ reports to include replacement reads and consumption adjustments as triggers for AQ revision along with the current qualifying read trigger for AQ calculation.
Changes to PCA interface (energy adjustments for telemetered sites) to record the creation date and time of energy adjustments for secondary trigger validation..

## Slide 13: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890S)
Detailed Design:
Scenario 1: Valid consumption adjustment received in the AQ submission window with an adjustment period falling partially with the current AQ relevant metered period, will be used to trigger an AQ revision.

## Slide 14: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890S)
Detailed Design:
Scenario 1b: Valid updated meter read received in the AQ submission window with read date with the current AQ relevant metered period, will be used to trigger an AQ revision.

## Slide 15: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890S)
Detailed Design:
Scenario 2: Valid consumption adjustment and a valid qualifying read received in the AQ submission window. The qualifying read will result in a new AQ calculation.

## Slide 16: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890)
Detailed Design:
Changes to monthly AQ calculation process
AQ calculation process is split into 3 sub processes –
  Valid AQ trigger data identification and retrieval based on AQ submission window
  Data Validation and End read determination for AQ process
  Start read determination and AQ calculation
Changes will be made to the above AQ sub processes while determining the primary AQ trigger for AQ calculation such that where the latest uploaded reading has either a valid accepted consumption adjustment (for class 4 sites) or a valid accepted updated meter reading (for class 3 and 4 sites) applied against it, it is still treated as a valid primary trigger for AQ calculation, in addition to the existing BAU primary triggers.
Changes will be made to include a new internal AQ trigger type for the AQ calculation process.

## Slide 17: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890)
Detailed Design:
Changes to AQ reports (internal and external)
Internal
Changes will be made to the monthly AQ validation report program (internal) to include the AQ revision checks in addition to the current AQ calculation validation steps.
Changes will be made to other internal AQ reports to ensure AQ revision values are also considered along with the calculated AQ values based on AQ trigger type.
External
Changes will be made to the Monthly AQ performance statistics report which feeds the external monthly AQ update pack published on Xoserve.com, to ensure AQ revision values are also included along with AQ calculations.
Changes will be made to the external MPRN Misuse report issued to PAC to include the new AQ methodology code for AQ revision (shown below).

## Slide 18: XRN5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (MOD0890)
Next Steps:
The DDCP was issued for formal consultation on 15th June 2026, consultation close out is w/c 29th June.
The DDCP will be subject to approval into delivery at the Change Management Committee on 8th July 2026.

## Slide 19
Section 4: Release/Project Updates
04
4a. XRN 5983 – February 26 Major release
4c. XRN 6065 – Minor Release 16
4b. XRN 6045 – June 26 Major Release

## Slide 20: XRN 5983 – February 26 Major release - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of February 26 Major Release was presented for approval at the ChMC meeting on 10/09/25. Overall release is tracking to target. Project was successfully implemented, 27/02/26, Post Implementation Support expected to complete 10/05/26. Progress Update: XRN5906, 5872, 5914/5922 are in Post implementation support (PIS) PIS and First usage is progressing to plan to complete 29/05/26 | Implementation date 27th February, contingency date 6th March | 
Risks and Issues | There is a risk that PIS exit is impacted due to the outstanding incident on the MPRN misuse report leading to a failure in PIS exit milestone. Mitigation a fix is scheduled to be implemented 29/05/26, the report will be run and validated by our BPC's post implementation of the fix |  | 
Costs | Changes are currently delivering with projected costs. |  | 
Scope | XRN5906 - Extending the PC4 Read Submission Window. XRN5872 - Updates to the AQ Amendments Process. XRN5914/XRN5922 - Shorten of the current LIS (Line in sand) date to 2-3 years & amend the LIS to rolling Period. |  | 
Complete
On Track
At Risk
Overdue

## Slide 21: XRN 6045 – June 26 Major Release- Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of June 26 Major Release was presented for approval at the ChMC meeting on 11/02/2026. Overall release is tracking to target; project is planned implement on 26/06/2026. Progress Update: June is tracking at Amber due to delays in testing. Work is ongoing on a replan to ensure the implementation date is not affected by these delays. XRN5805 has completed Build and System Testing and is in User Acceptance Testing phase. This was delayed due to Sustain 24 impacts and closure of System Tests. Team is working to bring this back in line with the plan XRN5702 has completed Build and System Testing and is in User Acceptance Testing phase. Team is working to complete all UAT in line with original planned dates. Training has been competed on the 19th May for both XRNs with a follow up planned for XRN5805 at DN Constituency on the 4th June. Decision in June ChMC: None | Implementation date 26th June 2026, contingency date 3rd July 2026 | 
Risks and Issues | N/A |  | 
Costs | Forecast to complete delivery against approved BER |  | 
Scope | XRN5702 – Update to assess the replacement of Facsimile as a form of communication (Modification 0864S) XRN5805 - Alternative Solution to address instances where VBA macros are present in DN Templates |  | 
Complete
On Track
At Risk
Overdue

## Slide 22: XRN 5702 – Update to assess the replacement of Facsimile as a form of communication (Modification 0864S)
DSG Update

## Slide 23: Change Background
Change XRN5702 has been raised to deliver the requirements of Modification 0864. Modification 0864 Update of UNC Code Communication Methods (removal of facsimile/fax) has been raised as it seeks to align obligated Code Communication methods with future communication network changes, attributable to national PSTN decommissioning, and the subsequent retirement of fax devices.
CDSP currently stores FAX as an alternate communication type received as part of registration requests and contact updates from Shippers. Post XRN5702 implementation, FAX will be rejected if received in as a communication type and Email (INT) will be accepted as an alternate communication type along with mandatory Telephone information.
The change is included in the scope of June 2026 major release and details, including the design, can be found here
Implementation of XRN5702 is planned for 26th June 2026.

## Slide 24: Impacting Data Reporting
  As per the change design, the CDSP was to publish to each Contract Manager a list of MPRNs that currently have associated fax details which will be removed as part of this change.
  The fax details report was shared to Contract Managers on 22nd May to highlight where MPRNs have FAX details associated to them within UK Link and, therefore, may require attention post implementation in line with UNC obligations.
  A second run of this report is planned for implementation. It is at this point that the FAX details held will be end dated. The report will be shared again for visibility of the MPRNs where associated FAX details have been end dated.
  A new monthly report will be generated on the 10th calendar day for Shippers and IGTs for sites with an AQ greater than 732,000kWh to provide increased visibility of the emergency contact detail position. These reports will be sent via email to Contract Managers.
Important Reminder to Shipper Users – UNC section Q 2.3.1 (c) will state, as a result of modification 0864S, that: “in the case of a Large Firm Supply Point the Annual Quantity of which is greater than 1,464,000 kWh (50,000 therms), one telephone number and one email address, for the purposes of receiving communications pursuant to this Section Q, which is able to receive transmissions 24 hours a day.

## Slide 25: File Format Changes
File(s) | Parent Record | Record | Data Attribute | Change
CNF, BRN, TNI, RCI, EMC, CFR, BRR, CTR, TRF, TMC, ASN, CRS, TRS, CSS | N/A | S67 | CONT_ELECTRONIC_COMM_TYPE | Description Change Only: ‘FAX’ is removed, and ‘INT’ (Email) is added as an allowable value.
SNO SNR | N/A | U87 | CONTACT_FAX_ NUMBER | File Format Structure Change: Field CONTACT_FAX_ NUMBER is removed
EQL EDL | N/A | B39 | ELA_IDENTITY | File Format Structure Change: ELA_IDENTITY -Field length increased to 241 to support Email
IDL IQL | N/A | B46 | CONT_ELECTRONIC_COMM_TYPE COMMUNICATION_IDENTITY | Description Change: CONT_ELECTRONIC_COMM_TYPE -‘FAX’ is removed, and ‘INT’ (Email) is added as an allowable value. File Format Structure Change: COMMUNICATION_IDENTITY - Field length increased to 241 to support Email
EWS | N/A | E24 | ELA_IDENTITY ELA_TYPE | File Format Structure Change: ELA_IDENTITY -Field length increased to 241 to support Email ELA_TYPE – ‘INT’ (Email) is added as an allowable value

## Slide 26: Training Pack
More information about the change can be found within the training pack that was delivered on the 19th May 2026.
A link to the training pack can be found here

## Slide 27: XRN 6065 – Minor Release 16 - Status Update
RAG Status | Overall Project RAG status |  | 
 | Schedule0 | Risks and Issues | Costs
 | Status Justification |  | 
Schedule | The scope of Minor Release 16 was presented for approval at the ChMC meeting on 08/04/26. Overall release is tracking at risk; Build projected to be completed on 29/05/26. Test preparation in progress, currently Amber due to BP24 Sustain delays moving environments delaying the start of ST. Progress Update: XRN 6081A Build completion in progress and is in Testing. Decision in June ChMC: None | Implementation date July 26 | 
Risks and Issues | Deferred Sustain implementation date will result in MiR 16 implementation dates being pushed back. Replan is being worked on to move Implementation date to July 26. |  | 
Costs | UK Link costs covered under Service and Operate funding |  | 
Scope | XRN 6081A – Meter Reading Service Improvement A - Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution |  | 
Complete
On Track
At Risk
Overdue

## Slide 28
Section 5:
Change Pipeline
05
Change Pipeline

## Slide 29: 2026 Forward View - Change Delivery Plan
January 26 – December 2026
Jan-26
June-26
February 26 – Major Release (XRN5983)
XRN5872 | XRN5906 | XRN5914 | XRN5922
March-26
Sep-26
Dec-26
June 26 – Major Release (XRN6045)
XRN5702 |XRN5805
Slide produced 29h July 2025
= Firm Implementation Date – Funding Approved by ChMC and / or Non-Negotiable Industry Implementation Date in place
= Indicative / Target Implementation Date – Changes are planned for delivery – Funding not yet approved by ChMC
= Implemented Change / Release
November 26 - Major Release (XRN 6095)
XRN5940| Meter Read Service Improvements (6081.C)
XRN5994 - Emergency Contact Data Service
Identifying Improvements to Meter Point Location Address Data Processes
XRN5968 | XRN5546
Minor Release 18
MiR17 - Service Improvements 6081.B
MiR16 – MR Service Improvements 6081.A
PIX
5924
XRN5941 – Performance Assurance Committee - Audit PAT
XRN6041 - CDSP Obligations required for the introduction of the Gas Shipper Obligation
XRN 5949 New Priority Consumer Category related to Community Heating (Phase 1)

## Slide 30: Change Delivery Plan – January 2026 – December 2026
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | Target Delivery Date | Release Type | Firm / Indicative
5872 | Mod0876S Updates to the Annual Quantity (AQ) amendment process | SEFE | Shipper DN | Shipper | £190k | 27 February 2026 | Major | Firm
5906 | Mod0884 – Extending the PC4 Read Submission Window | OVO | Shipper DN IGT | Shipper DN | £105k | 27 February 2026 | Major | Firm
5914 5922 | Mod0886 - Amend the Code Cut-Off Date to a Rolling Period Mod0896 – Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | SSE SEFE | Shipper DN IGT | Shipper | £90k | 27 February 2026 | Adhoc / Major | Firm
5941 | Performance Assurance Committee – Audit PAT | Xoserve | Shipper DN IGT | Shipper DN IGT | £300K | TBC | Adhoc | Indicative
5702 | Mod0864S - Update to assess the replacement of Facsimile as a form of communication | NGT | All DSC Customers | Shipper DN | £158k | 26 June 2026 | Major | Firm
5805 | Alternative Solution to address instances where VBA macros are present in DN Templates | WWU | DN | DN | £160k | 26 June 2026 | Major | Firm
5924 | Physical Information Exchange (PIX) Ongoing Support Options | Xoserve | All | TBC | N/A | 31 June 2026 | Adhoc | Firm
6081 A | Meter Read Service Improvements Part A Fix Historic NDM Check to Check Reconciliation Periods - Tactical Solution | Xoserve | Shipper DN | N/A | N/A | July 2026 | Minor | Indicative
5994 | Emergency Contact Validation Service | Cadent | Shipper DN | TBC | £170k | August 2026 | Adhoc | Indicative
6081 B | Meter Read Service Improvements Part B Reconciliation of Multiple Read Replacements – Historic Reporting and Tactical Solution | Xoserve | Shipper DN | N/A | N/A | September 2026 | Minor | Indicative
5949 | New Priority Consumer Category related to Community Heating (Phase 1) | NGT | All DSC Customers | TBC | £230k | September 2026 | Adhoc | Indicative
5940 | Mod0890 – Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation | Centrica | Shipper DN | TBC | £270k | 6 November 2026 | Major | Indicative
6081C | Meter Read Service Improvements – Part C NDM Check to Check Reconciliation – Enduring Solution | Xoserve | Shipper DN | Shipper DN | £110K | 6 November 2026 | Major | Indicative
6041 | UNC Modification 0922 (IGT UNC Modification 180) – CDSP Obligations required for the introduction of the GSO | CDSP | ALL DSC Parties | TBC | TBC | December 2026 | Adhoc | Indicative

## Slide 31: Change Backlog – Priority Service Changes ‘In Progress’
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | June 26 - ChMC Update
6001 | Modification 0909 - Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures | SEFE | Shipper DN | Shipper DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification – DDP delivery expected and will move to backlog once validated with delivery team.
6000 | Modification 0908 – Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading by a Shipper | WWU | Shipper DN IGT | DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification which has been approved. Transition arrangements being discussed ahead of agreeing implementation approach.
5972 | CDSP provisions to support new Supplier Deed of Undertaking (DoU) Licence Condition (9a) | Cadent | DN IGT | DN | Requirements | Change Proposal raised on behalf of DNs to ensure new Deed of Undertaking arrangements are put in place with Supplier organisations. Analysis on Invoicing processes (charge types) to be performed and validated with DNs.
5987 | Modification 0915 – Debt Relief Scheme Payment (DRSP) | NGN | Shipper DN IGT | NGT DN | Requirements | CDSP will be actively supporting Modification development over proceeding months ahead of baselining requirements. Awaiting Ofgem decision ahead of planning delivery activities.
6079 | UNC 0926S Maintenance criteria for Emergency Contact data held in Central Systems | Cadent | Shipper DN IGT | Shipper DN | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
6067 | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894) | Cadent | Shipper DN NGT | TBC | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification
6066 | Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression (Modification 0894A) | National Gas Transmission | Shipper DN NGT | TBC | Requirements | Change Proposal created to enable CDSP solution to be progressed in adherence to the related UNC Modification

## Slide 32: Change Backlog – Remaining Changes ‘In Progress’
XRN | Change Title | Proposer | Benefit / Impact | Funding | Status | June 26 - ChMC Update
5473 | Meter Asset Comparison Service | CDSP | Shipper | Shipper | Solution Assessment | Issued out for consultation – preferred option will be progressed through the relevant delivery path (e.g. DDP Release)
5569 | Contact Data Provision for IGT Customers | BUUK | IGT | IGT | Solution Assessment | Solution Option issued for consultation in May ‘25 Change Pack – next steps to be confirmed following change pack decision and agreement on how to progress.
5810 | Theft of Gas (ToG) DN Calculation Tool | Cadent | DN | DN | Solution Assessment | Protype solution being trialled with one DN party ahead of finalising functionality and sharing with all DN parties. Workshop arranged 3rd October. Continue to monitor progress with DNs before reaching agreement that change can be closed. Target July 2026.
5950 | DSC Invoice Number generation review | CDSP | Shipper DN NGT | TBC | Solution Assessment | Re-assigned to change backlog as change is not time critical and will require customer notification period prior to delivery. Solution Option Change Pack targeted in June.
5955 | Private networks duplicate MPRNs - options for long-term fix | Cadent | DN | DN | Solution Assessment | Re-assigned to change backlog ahead of Solution Option Change Pack being published in July for consultation. Re-planned due to increased Priority Service change demand.
5968 | Identifying improvements to Meter Point Location Address Data processes | Cadent | DN | DN | Analysis | Parent Change Proposal raised to perform analysis and make recommendations on changes that can be implemented to the Address Amendment process.
6039 | Provision of IGT SMP Data to DNs | NGN | DN IGT | DN | Requirements | Change Proposal raised to progress solutions that enable DNs the ability to receive IGT SMP data. Requirements definition has commenced and solution assessment due to take place in June.
6056 | Introduction of new Supply Meter Point status of ‘IS’ (Isolation) - Cleanse and remove obsolete ‘CL’ (Clamped) status | Cadent | DN IGT Shipper | DN | Requirements | New Change Proposal raised to progress solution that enables DNs and other industry stakeholders the ability to acknowledge a Supply Meter Point Status of Isolation. Target June 2027 Implementation, subject to relevant approvals.

## Slide 33: Change Backlog – ‘On Hold’ Details
XRN | Change Title | Proposer | Benefit / Impact | Funding | HLSO Max Cost | May 26 ChMC Update
5616 | CSEP Annual Quantity Capacity Management | WWU | DN IGT Shipper | DN IGT | *£260k revised following design | Agreed following August bi-party CSEP meeting that change will remain on hold whilst data cleansing activities were progressed.
5546 | Resolution of Address Interactions between DCC and CDSP | Xoserve | DN IGT Shipper | Shipper | N/A | N/A – performing analysis on data extracts provided by DCC Incorporate findings into Address Management Project (XRN5968)
5471 | DSC Core Customer Access to Data | CDSP | Shipper DN IGT | IGT Shipper DN | TBC | Low Priority – CDSP raised Change Proposal
5806 | CDSP Solution to enable exit of application of User Premises Termination Notice (UPTN) | NGT | All DSC Customers | TBC | TBC | Change Proposal raised to analyse process and solution impacts that may be necessary to facilitate exit – analysis being planned in with relevant resource

## Slide 34: DSC Change Pack Consultation Plan (two-month view)
June – 26
July - 26
Aug – 26
XRN5955 - Private networks duplicate MPRNs - options for long-term fix
Key
= Design Change Pack for Consultation
= Solution Option Change Pack for Consultation
= For Information Change Pack
XRN5950 - DSC Invoice Number generation review
XRN 5940 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month (Modification 0890)
XRN 5949 - New Priority Consumer Category related to Community Heating (Phase 1)

## Slide 35
Section6: AOB
06
XRN 5702 Update to assess the replacement of Facsimile as a form of communication (Modification 0864S)

## Slide 36
Section 7:
Annex
07
7a. ChMC Update
7b. Rec Update
7c. POAP